## Sheet1
Task ID | Task Name | Task Description | STATUS | Person in Charge | Start Date | End Date | Duration | % Complete | Risk Status | Actual Completion Date | Result | Notes
1 | Lập Page | n/a | DONE | Lê Hoàng Nam | 2024-01-11 | 2024-01-11 | 1 day | 100% | n/a | n/a | Link
2 | Up Logo | n/a | DONE | Lê Hoàng Nam | 2024-01-11 | 2024-01-11 | 1 day | 100% | n/a | n/a | Link
3 | Post giới thiệu dự án | n/a | DONE | Nguyễn Hoàng Việt | 2024-01-11 | 2024-01-11 | 1 day | 100% | n/a | n/a | Link
4 | Up ảnh bìa | n/a | DONE | Lê Hoàng Nam | 2024-01-12 | 2024-01-12 | 1 day | 100% | n/a | n/a | Link
5 | Up nhạc #1 | n/a | DONE | Lê Hoàng Nam | 2024-01-14 | 2024-01-14 | 1 day | 100% | n/a | n/a | Link
6 | Ý tưởng chữa lành | n/a | DONE | Huỳnh Quốc Trung | 2024-01-14 | 2024-01-14 | 1 day | 100% | n/a | n/a | Link
7 | Up nhạc #2 | n/a | DONE | Lê Hoàng Nam | 2024-01-15 | 2024-01-15 | 1 day | 100% | n/a | n/a | Link
8 | Từ điển hạnh phúc: Intro | n/a | DONE | Lê Hoàng Nam | 2024-01-18 | 2024-01-18 | 1 day | 100% | n/a | n/a | Link
9 | Up nhạc #3 | n/a | DONE | Nguyễn Hữu Hoài | 2024-01-18 | 2024-01-18 | 1 day | 100% | n/a | n/a | Link
10 | Post hạnh phúc bền vững | n/a | DONE | Lê Hoàng Nam | 2024-01-21 | 2024-01-21 | 1 day | 100% | n/a | n/a | Link
11 | Tìm kiếm hạnh phúc qua những hành động nhỏ bé | n/a | DONE | Lê Hoàng Nam | 2024-01-24 | 2024-01-24 | 1 day | 100% | n/a | n/a | Link
12 | Up nhạc #4 | n/a | DONE | Nguyễn Hữu Hoài | 2024-01-24 | 2024-01-24 | 1 day | 100% | n/a | n/a | Link
13 | Từ điển hạnh phúc #1 | n/a | DONE | Lê Hoàng Nam | 2024-01-25 | 2024-01-25 | 1 day | 100% | n/a | n/a | Link
14 | Trích dẫn tôn giáo #1 | n/a | DONE | Nguyễn Hoàng Việt | 2024-01-25 | 2024-01-25 | 1 day | 100% | n/a | n/a | Link
15 | Trích dẫn chữa lành: Nóng giận là bản lĩnh | n/a | DONE | Huỳnh Quốc Trung | 2024-01-26 | 2024-01-26 | 1 day | 100% | n/a | n/a | Link
16 | Từ điển hạnh phúc #2 | n/a | DONE | Nhữ Quang Anh | 2024-01-27 | 2024-01-27 | 1 day | 100% | n/a | n/a | Link
17 | Stress là gì ? | n/a | DONE | Lê Hoàng Nam | 2024-01-28 | 2024-01-28 | 1 day | 100% | n/a | n/a | Link
18 | Trích dẫn tôn giáo #2 | n/a | DONE | Nguyễn Hoàng Việt | 2024-01-28 | 2024-01-28 | 1 day | 100% | n/a | n/a | Link
19 | Up nhạc #5 | n/a | DONE | Nguyễn Hữu Hoài | 2024-01-28 | 2024-01-28 | 1 day | 100% | n/a | n/a | Link
20 | Từ điển hạnh phúc #3 | n/a | DONE | Lê Hoàng Nam | 2024-01-29 | 2024-01-29 | 1 day | 100% | n/a | n/a | Link
21 | Up nhạc #6 | n/a | DONE | Nguyễn Hữu Hoài | 2024-01-30 | 2024-01-30 | 1 day | 100% | n/a | n/a | Link
22 | Chữa lành từ nỗi đau | n/a | DONE | Huỳnh Quốc Trung | 2024-01-30 | 2024-01-30 | 1 day | 100% | n/a | n/a | Link
23 | Trích dẫn tôn giáo #3 | n/a | DONE | Nguyễn Hoàng Việt | 2024-02-01 | 2024-02-01 | 1 day | 100% | n/a | n/a | Link
24 | Up nhạc #7 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-02 | 2024-02-02 | 1 day | 100% | n/a | n/a | Link
25 | Trích dẫn chữa lành: Hiểu về trái tim | n/a | DONE | Huỳnh Quốc Trung | 2024-02-03 | 2024-02-03 | 1 day | 100% | n/a | n/a | Link
26 | Chữa lành không khó: Intro | n/a | DONE | Nguyễn Trần Trường Chinh | 2024-02-04 | 2024-02-04 | 1 day | 100% | n/a | n/a | Link
27 | Những điều tuyệt vời tan chảy trái tim bạn | n/a | DONE | Võ Quang Triều | 2024-02-05 | 2024-02-05 | 1 day | 100% | n/a | n/a | Link
28 | Từ điển hạnh phúc #4 | n/a | DONE | Nhữ Quang Anh | 2024-02-05 | 2024-02-05 | 1 day | 100% | n/a | n/a | Link
29 | Up nhạc #8 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-05 | 2024-02-05 | 1 day | 100% | n/a | n/a | Link
30 | Từ điển hạnh phúc #5 | n/a | DONE | Nhữ Quang Anh | 2024-02-06 | 2024-02-06 | 1 day | 100% | n/a | n/a | Link
31 | Phiên chợ 0 đồng | n/a | DONE | Lê Hoàng Nam | 2024-02-06 | 2024-02-06 | 1 day | 100% | n/a | n/a | Link
32 | Tìm kiếm hạnh phúc qua những hành động nhỏ bé #2 | n/a | DONE | Lê Hoàng Nam | 2024-02-06 | 2024-02-06 | 1 day | 100% | n/a | n/a | Link
33 | Up nhạc #9 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-06 | 2024-02-06 | 1 day | 100% | n/a | n/a | Link
34 | Từ điển hạnh phúc #6 | n/a | DONE | Lê Hoàng Nam | 2024-02-07 | 2024-02-07 | 1 day | 100% | n/a | n/a | Link
35 | Up nhạc #10 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-07 | 2024-02-07 | 1 day | 100% | n/a | n/a | Link
36 | Trích dẫn tôn giáo #4 | n/a | DONE | Nguyễn Hoàng Việt | 2024-02-08 | 2024-02-08 | 1 day | 100% | n/a | n/a | Link
37 | Up nhạc #11 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-08 | 2024-02-08 | 1 day | 100% | n/a | n/a | Link
38 | Project Management File | n/a | DONE | Lê Hoàng Nam | 2024-02-09 | 2024-02-09 | 1 day | 100% | n/a | n/a | Link
39 | Hành trình diệu kỳ với Tết | n/a | DONE | Lê Hoàng Nam | 2024-02-09 | 2024-02-09 | 1 day | 100% | n/a | n/a | Link
40 | Countdown New Year | n/a | DONE | Lê Hoàng Nam | 2024-02-09 | 2024-02-09 | 1 day | 100% | n/a | n/a | Link
41 | Up Nhạc #12 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-09 | 2024-02-09 | 1 day | 100% | n/a | n/a | Link
42 | Sự thật thú vị ngẫu nhiên #1 | n/a | DONE | Lê Hoàng Nam | 2024-02-10 | 2024-02-10 | 1 day | 100% | n/a | n/a | Link
43 | Up Nhạc #13 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-10 | 2024-02-10 | 1 day | 100% | n/a | n/a | Link
44 | Sự thật thú vị ngẫu nhiên #2 | n/a | DONE | Lê Hoàng Nam | 2024-02-11 | 2024-02-11 | 1 day | 100% | n/a | n/a | Link
45 | những câu nói chữa lành tâm hồn bạn | n/a | DONE | Võ Quang Triều | 2024-02-11 | 2024-02-11 | 1 day | 100% | n/a | n/a | Link
46 | Up Nhạc #14 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-11 | 2024-02-11 | 1 day | 100% | n/a | n/a | Link
47 | Chữa lành không khó: Nghệ thuật | n/a | DONE | Nguyễn Trần Trường Chinh | 2024-02-11 | 2024-02-11 | 1 day | 100% | n/a | n/a | Link
48 | Sự thật thú vị ngẫu nhiên #3 | n/a | DONE | Lê Hoàng Nam | 2024-02-12 | 2024-02-12 | 1 day | 100% | n/a | n/a | Link
49 | Up Nhạc #15 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-12 | 2024-02-12 | 1 day | 100% | n/a | n/a | Link
50 | Sự thật thú vị ngẫu nhiên #4 | n/a | DONE | Lê Hoàng Nam | 2024-02-13 | 2024-02-13 | 1 day | 100% | n/a | n/a | Link
51 | Sự thật thú vị ngẫu nhiên #5 | n/a | DONE | Lê Hoàng Nam | 2024-02-14 | 2024-02-14 | 1 day | 100% | n/a | n/a | Link
52 | Up Nhạc #16 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-14 | 2024-02-14 | 1 day | 100% | n/a | n/a | Link
53 | Sự thật thú vị ngẫu nhiên #6 | n/a | DONE | Lê Hoàng Nam | 2024-02-15 | 2024-02-15 | 1 day | 100% | n/a | n/a | Link
54 | Up Nhạc #17 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-15 | 2024-02-15 | 1 day | 100% | n/a | n/a | Link
55 | Sự thật thú vị ngẫu nhiên #7 | n/a | DONE | Lê Hoàng Nam | 2024-02-16 | 2024-02-16 | 1 day | 100% | n/a | n/a | Link
56 | Sự thật thú vị ngẫu nhiên #8 | n/a | DONE | Lê Hoàng Nam | 2024-02-17 | 2024-02-17 | 1 day | 100% | n/a | n/a | Link
57 | Up Nhạc #18 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-17 | 2024-02-17 | 1 day | 100% | n/a | n/a | Link
58 | Hãy chia sẻ cảm xúc của bạn | n/a | DONE | Võ Quang Triều | 2024-02-18 | 2024-02-18 | 1 day | 100% | n/a | n/a | Link
59 | Chữa lành không khó: Tận hưởng thiên nhiên | n/a | DONE | Nguyễn Trần Trường Chinh | 2024-02-18 | 2024-02-18 | 1 day | 100% | n/a | n/a | Link
60 | Sự thật thú vị ngẫu nhiên #9 | n/a | DONE | Lê Hoàng Nam | 2024-02-18 | 2024-02-18 | 1 day | 100% | n/a | n/a | Link
61 | Up Nhạc #19 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-18 | 2024-02-18 | 1 day | 100% | n/a | n/a | Link
62 | Sự thật thú vị ngẫu nhiên #10 | n/a | DONE | Lê Hoàng Nam | 2024-02-19 | 2024-02-19 | 1 day | 100% | n/a | n/a | Link
63 | Up Nhạc #20 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-19 | 2024-02-19 | 1 day | 100% | n/a | n/a | Link
64 | Sự thật thú vị ngẫu nhiên #11 | n/a | DONE | Lê Hoàng Nam | 2024-02-20 | 2024-02-20 | 1 day | 100% | n/a | n/a | Link
65 | Hành trình của Aiko Intro | n/a | DONE | Lê Hoàng Nam | 2024-02-20 | 2024-02-20 | 1 day | 100% | n/a | n/a | Link
66 | Hành trình của Aiko Chương 1 | n/a | DONE | Lê Hoàng Nam | 2024-02-20 | 2024-02-20 | 1 day | 100% | n/a | n/a | Link
67 | Trích dẫn tôn giáo #5 | n/a | DONE | Nguyễn Hoàng Việt | 2024-02-20 | 2024-02-20 | 1 day | 100% | n/a | n/a | Link
68 | Sự thật thú vị ngẫu nhiên #12 | n/a | DONE | Lê Hoàng Nam | 2024-02-21 | 2024-02-21 | 1 day | 100% | n/a | n/a | Link
69 | Hành trình của Aiko Chương 2 | n/a | DONE | Lê Hoàng Nam | 2024-02-21 | 2024-02-21 | 1 day | 100% | n/a | n/a | Link
70 | Up Nhạc #21 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-21 | 2024-02-21 | 1 day | 100% | n/a | n/a | Link
71 | Up Nhạc #22 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-22 | 2024-02-22 | 1 day | 100% | n/a | n/a | Link
72 | Sự thật thú vị ngẫu nhiên #13 | n/a | DONE | Lê Hoàng Nam | 2024-02-22 | 2024-02-22 | 1 day | 100% | n/a | n/a | Link
73 | Trích dẫn tôn giáo #6 | n/a | DONE | Nguyễn Hoàng Việt | 2024-02-22 | 2024-02-23 | 1 day | 100% | n/a | n/a | Link
74 | Những lời nói tiếp sức cho bạn | n/a | DONE | Võ Quang Triều | 22/0202024 | 2024-02-22 | 1 day | 100̀ | n/a | n/a | Link
75 | Sự thật thú vị ngẫu nhiên #14 | n/a | DONE | Lê Hoàng Nam | 2024-02-23 | 2024-02-23 | 1 day | 100% | n/a | n/a | Link
76 | Hành trình của Aiko Chương 2 | n/a | DONE | Lê Hoàng Nam | 2024-02-23 | 2024-02-23 | 1 day | 100% | n/a | n/a | Link
77 | Up Nhạc #23 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-23 | 2024-02-23 | 1 day | 100% | n/a | n/a | Link
78 | Up Nhạc #24 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-24 | 2024-02-24 | 1 day | 100% | n/a | n/a | Link
79 | Chữa lành không khó: Đọc sách để thấy thoải mái hơn | n/a | DONE | Nguyễn Trần Trường Chinh | 2024-02-25 | 2024-02-25 | 1 day | 100% | n/a | n/a
80 | Up Nhạc #25 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-25 | 2024-02-25 | 1 day | 100% | n/a | n/a | Link
81 | Sự thật thú vị ngẫu nhiên #15 | n/a | DONE | Lê Hoàng Nam | 2024-02-26 | 2024-02-25 | 1 day | 100% | n/a | n/a | Link
82 | Hành trình của Aiko Chương 3 | n/a | DONE | Lê Hoàng Nam | 2024-02-26 | 2024-02-26 | 1 day | 100% | n/a | n/a | Link
83 | Sự thật thú vị ngẫu nhiên #16 | n/a | DONE | Lê Hoàng Nam | 2024-02-26 | 2024-02-26 | 1 day | 100% | n/a | n/a | Link
84 | Hành trình của Aiko Chương 4 | n/a | DONE | Lê Hoàng Nam | 2024-02-26 | 2024-02-26 | 1 day | 100% | n/a | n/a | Link
85 | Sự thật thú vị ngẫu nhiên #17 | n/a | DONE | Lê Hoàng Nam | 2024-02-26 | 2024-02-26 | 1 day | 100% | n/a | n/a | Link
86 | Up Nhạc #26 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-26 | 2024-02-26 | 1 day | 100% | n/a | n/a | Link
87 | Hành trình của Aiko Chương 5 | n/a | DONE | Lê Hoàng Nam | 2024-02-27 | 2024-02-27 | 1 day | 100% | n/a | n/a | Link
88 | Sự thật thú vị ngẫu nhiên #18 | n/a | DONE | Lê Hoàng Nam | 2024-02-27 | 2024-02-27 | 1 day | 100% | n/a | n/a | Link
89 | Hành trình của Aiko Chương 6 | n/a | DONE | Lê Hoàng Nam | 2024-02-27 | 2024-02-27 | 1 day | 100% | n/a | n/a | Link
90 | Up Nhạc #27 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-27 | 2024-02-27 | 1 day | 100% | n/a | n/a | Link
91 | Up Nhạc #28 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-28 | 2024-02-28 | 1 day | 100% | n/a | n/a | Link
92 | Up Nhạc #29 | n/a | DONE | Nguyễn Hữu Hoài | 2024-02-29 | 2024-02-29 | 1 day | 100% | n/a | n/a | Link
93 | Sự thật thú vị ngẫu nhiên #19 | n/a | DONE | Lê Hoàng Nam | 2024-02-28 | 2024-02-28 | 1 day | 100% | n/a | n/a | Link
94 | Âm nhạc #1 | n/a | DONE | Lê Hoàng Nam | 2024-02-28 | 2024-02-28 | 1 day | 100% | n/a | n/a | Link
95 | Âm nhạc #2 | n/a | DONE | Lê Hoàng Nam | 2024-02-29 | 2024-02-29 | 1 day | 100% | n/a | n/a | Link
96 | Sự thật thú vị ngẫu nhiên #20 | n/a | DONE | Lê Hoàng Nam | 2024-02-29 | 2024-02-29 | 1 day | 100% | n/a | n/a | Link
97 | Up Nhạc #30 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-02 | 2024-03-02 | 1 day | 100% | n/a | n/a | Link
98 | Luôn tin tưởng chính mình | n/a | DONE | Võ Quang Triều | 2024-03-03 | 2024-03-03 | 1 day | 100% | n/a | n/a | Link
99 | Chữa lành không khó: Chăm sóc thú cưng | n/a | DONE | Nguyễn Trần Trường Chinh | 2024-03-03 | 2024-03-03 | 1 day | 100% | n/a | n/a | Link
100 | Up Nhạc #31 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-03 | 2024-03-03 | 1 day | 100% | n/a | n/a | Link
101 | Up Nhạc #32 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-04 | 2024-03-04 | 1 day | 100% | n/a | n/a | Link
102 | Up Nhạc #33 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-05 | 2024-03-05 | 1 day | 100% | n/a | n/a | Link
103 | Up Nhạc #34 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-06 | 2024-03-06 | 1 day | 100% | n/a | n/a | Link
104 | Up Nhạc #35 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-07 | 2024-03-07 | 1 day | 100% | n/a | n/a | Link
105 | Up Nhạc #36 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-08 | 2024-03-08 | 1 day | 100% | n/a | n/a | Link
106 | Up Nhạc #37 | n/a | DONE | Nguyễn Hữu Hoài | 2024-03-09 | 2024-03-09 | 1 day | 100% | n/a | n/a | Link
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200